## CTR
Deliverable | Detail | Notes (FEA) | Time estimate to deliver (hours) | Rate ( £/hr ) | Base cost (£)
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • Review of cable optimisation algorithm to convert to cost not simply length. There are a large number of different approaches that can be taken with the optimisation algorithm for the array cable layout. Undertake a literature review to identify the different approaches, see whether there is any consensus on what the metrics for assessing the performance of them and likewise whether there is any consensus on what is the best optimisation approach. Starting point for assessment: a. Near optimality of solution b. Computational efficiency Below are some initial suggestions for the review: 1. A review of offshore wind farm layout optimization and electrical system design methods - Details a number of different optimisation algorithms for the array cables and puts it in the context of the whole wind farm 2. Global Optimization of Offshore Wind Farm Collection Systems 3. Offshore wind farm electrical design_a review - This contains the most comprehensive reference to optimisation approaches that I've been able to find. 4. Offshore wind farm layout optimization using mathematical programming languages 5. Offshore wind farm layout optimization using particle swarm optimization 6. Optimisation of offshore wind farm collection systems-based on modified genetic algorithm 7. Optimization for Offshore Wind Farm Cable Connection Layout using APSO-MST Method 8. Optimizing wind farm cable routing considering power losses Final deliverable would be a summary of the review of the literature, recommnedation for an optimiation approach and then deployment within WFLO | Lit review (2 days), algorithm development (5 days). Integration with current tool (2 days). Total 72 hours | 72 | 75 | 5400
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • Incorporation of electrical losses by merging the logic of a spreadsheet (to be provided) into the cable optimsiation algorithm. Incorporate the assessment of the OPEX of a layout and cable size selection based on the standardised calculation method described within IEC60287-1-1: Current rating equations (100%) load factor and calculation of losses and IEC60287-3-2: Economic optimisation of power cables. Validation of the derived load factors and losses for a selection of 5 cable sizes to be included | This may effect the choice of optimisation, so is co-dependent on some of the above. Adding additional parameters into the optimisation (1.5 days), depending on requirements for user interface with parameters (0.5 to 1.5 days). Total 24 hours | 24 | 75 | 1800
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • Constraint that array cables should not be able to cross each other. There should also be a threshold distance (available as a parameter) that is the closest two cables can be from one another (except for at the substation or WTGs). For example 50m. Threshold distance to allow for parallel runs of cable. Stings 4 & 5 on EA1 are an example. There is some description of how this could be done within "Optimizing wind farm cable routing considering power losses" where they talk about Steiner nodes. | + 2 days on other development? | 16 | 75 | 1200
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • Additional parameter for export cable route so array cable routes do not cross the export cable route. |  | 8 | 75 | 600
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • Ability to run array cable optimisation aspect in isolation from the rest of the tool, based on a fixed WTG layout input. Often the use case is that the WTG layout has already been developed and the cables team needs to generate an array cable layout. | Depends on the user requirements. Minimum 2 days to copy current outputs and have inputs separate from the rest of the tool (if required). Might be better to develop separate tool with single page….? | 16 | 75 | 1200
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • It may be the case that for performance issues, there would need to be a simple and complex version of the algorithm - simple to be run witheth global optimisation; complex to be run on it's own (will need to do some testing to see how improving the array cable routine impacts preformance). Some of the papers referenced in C6 provide description of how this can be done. | Agreed. Will depend on findings from lit review. See comment above on separate tool. Could potentially look at including different optimisation algorithms in single standalone tool and best/quickest from testing of these be integrated into the main tool. Time depending on the range of algorithms tested. Best to estimate after lit review. | 16 | 75 | 1200
Optimisation of the cable/substation layout. Rewrite the cable module so that the cable layouts produced are more realistic and can be used as an input to preliminary design. | • Optimisation of the substation location: from a fixed set of WTGs + unallocated OSS position (s), be able to determine which position is the optimal one for the substation based on cable length and substation foundation cost. Would need to add in a parameter for substatation location cost. | How would the cost of OSS be determined, would it be similar to the WTG cost i.e. based on a depth/other cost surface? | 16 | 75 | 1200
Design of WTG location optimisation algorithm | • Enable regular grid layouts with 2 lines of orientation | 16 hours | 16 | 75 | 1200
Design of WTG location optimisation algorithm | • Enable evaluation of irregular inter row / column spacing. Rows of WTGs in a layout to have uneven gaps between them (e.g. 1000m 1100m, 1400m etc). This is something that the GIS team are sometimes asked to do manually and can help with avoiding certain constraints. | Would likely need to introduce more parameters to achieve this. Maybe just one if just linear increase in spacing and rest can be handled with orientation angle. Depends how prescriptive it needs to be i.e. do the GIS team need to be able to specify exact widths or do you want to optimise over variable widths? (8 hours if not prescriptive) | 16 | 75 | 1200
Design of WTG location optimisation algorithm | • Explore other layout building options: Layout with turbine density at periphery, layouts based in non-straight lines geometries (curved layout), etc. | Completely depends on what transformations are tested | 40 | 75 | 3000
Design of WTG location optimisation algorithm | • Ability to create layouts non restricted by polygon limits (may need to add some additional parameters to drive the size of the layout). | Likely to require redeisgn of input data processing and change to algorithm. 1 day + 3 days (32 hours) | 32 | 75 | 2400
Optimization process | • Optimize regardless of layout type (regular, fanned, edge weighted etcetera) | 3 days | 24 | 75 | 1800
Management of different turbine type | • Tool enables changing easily and managing different type of turbine (for example providing turbine file at openwind format as input and calling the file from Openwind), | To be able to manage OpenWind inputs JUST via the tool may not be possible. Changing the turbine type if already setup in OpenWind is pretty much already done | 3 | 75 | 225
Management of number of WTG | • Improve management of number of turbines modelled (depending on OpenWind capabilities and bug fixes for this) and comparing farm capacity (pending on SPR being able to provide a financial model for that). | The site max capacity parameter I don't believe is currently being used, but could be used to optimise for number of turbines and layout rather than target number. 1 day back end 1 day front end | 16 | 75 | 1200
Management of number of WTG | • comparing layout option with different farm capacity (depending on SPR being able to provide a financial model for that, i.e effect of LCOE to add or remove turbines). | +1 day on above | 8 | 75 | 600
Effective turbulence check | • Add effective turbulence check (either through Openwind or SPR provided algorithm in python) | Depends on how this is done | 4 | 75 | 300
Micrositing | • Enable ability to run a micrositing routine to shift positions within a threshold (e.g. 100m) to identify the optimum WTG locations with the most favourable groud conditions outside that are outside of exclusion zones. Purpose is to avoid localised constraints where a WTG may be placed (e.g. sand waves). This may require the inclusion of an additional constraint layer which captures the localised constraints for micrositing. | This would likely require a new optimisation approach that is secondary to current optimisation. 7 days for new optimisation routine and 2 to add to front end and results | 72 | 75 | 5400
Results, projects and database management | •Improve searching and filtering of results options, database management.to efficiently manage numerous runs, different wind farm projects and exchange datafiles. | Needs further scoping, but may require some fundamental changes to current code 7 days | 56 | 75 | 4200
Get the tool properly deployed on the VM | •Ensure tool can be fully deployed in an offline environement. |  | 12 | 75 | 900
Bug shooting and acceptance | •Support with bug fixes and functional issues identified during user testing and validation. | Hard to estimate | 80 | 75 | 6000
Provide software support for the tool | •Ad hoc support with bugs and functional issues during tool use | Hard to estimate | 80 | 75 | 6000
SUB TOTAL |  |  | 627 |  | 47025